## Sheet4
Secure Bank Mobile Check Deposit Project : Stakeholders Risks
Risk Category | Risk Statement | Likelihood | Impact | Mitigation Strategies | Risk Owner | Stakeholder Risks Heatmap
Technical/ Execution | Integration Complexity: The complexity of integrating the mobile check deposit feature with legacy systems may delay the project timeline, increase costs, and reduce quality. | High | High | Conduct early technical reviews, iterative testing, and adopt agile methodologies. Establish contingency plans and cross-functional troubleshooting teams. | IT/Development Team |  | High | Regulatory Non-Compliance & PIPEDA Breach AML Detection Gaps Cyberattacks/Data Breaches | System Failures Low ROI if Adoption is Slow Increase in Check Fraud Cases | Integration Complexity Low Adoption Due to Poor Usability
Technical/ Execution | System Failures: Unexpected system failures, including hardware or software breakdowns, may disrupt check deposit processing. This disruption could result in significant delays and customer inconvenience, affecting operations and customer service. | Medium | High | Implement robust monitoring, scheduled maintenance, and backup systems. Set up rapid-response protocols for system recovery. | IT Operations | IMPACT | Medium | Negative Reviews Impacting Reputation | Staff Resistance Internal Coordination Gaps Scope Creep & Cost Overruns | Image Recognition Failure
Technical/ Execution | Image Recognition Failure: Failure of image recognition algorithms to accurately process checks may result in deposit errors which could require reprocessing and negatively impact IT, Quality assurance and customer satisfaction. | High | Medium | Perform rigorous testing of algorithms. Refine models with iterative improvements. Set up fallback manual verification processes. | Quality Assurance (QA) |  | Low | Minor System Hiccups Communication Gaps Minor Regulatory Changes |  | Vendor Delays Minor UI Issues
Operational Risks | Staff Resistance: Branch staff may resist changes due to perceived workload shifts and role changes and could slow operational efficiency and delay digital adoption. | Medium | Medium | Implement comprehensive training and change management initiatives. Engage staff early with clear communication and incentives. | Branch Operations Manager |  |  | Low | Medium | High
Operational Risks | Internal Coordination Gaps: Lack of effective coordination between departments could lead to miscommunications. These gaps could cause project delays and suboptimal resource utilization, affecting project managers and team leads. | Medium | Medium | Hold regular cross-functional meetings. Utilize collaborative project management tools. Clearly document roles and responsibilities. | Project Manager |  |  | LIKELIHOOD
Financial Risks | Scope Creep & Cost Overruns: Uncontrolled changes in project scope may lead to additional, unplanned costs. This could result in budget overruns and affect overall ROI—impacting the CFO's financial oversight and Project Manager's execution. | Medium | Medium | Enforce strict scope management and change control processes. Set aside contingency budgets; conduct periodic financial reviews. | Project Manager & CFO
Financial Risks | Low ROI if Adoption is Slow: Slow customer adoption of the mobile deposit feature which could lead to lower-than-expected digital revenue growth and diminished returns. | Medium | High | Launch targeted marketing and user training initiatives. Monitor adoption rates closely. Implement iterative improvements based on customer feedback. | Marketing Team
Compliance/ Regulatory | Regulatory Non-Compliance & PIPEDA Breach: Failure to meet regulatory requirements (including PIPEDA standards) due to oversight or delays. This may result in legal penalties and significant reputational damage. | Low | High | Schedule regular compliance audits. Maintain updated documentation. Engage legal counsel and provide ongoing staff training on regulatory requirements. | Compliance Officer
Compliance/ Regulatory | AML Detection Gaps: Inadequate fraud detection may allow fraudulent checks to bypass controls, increasing anti-money laundering risks and regulatory scrutiny. | Low | High | Enhance fraud detection systems with machine learning; conduct periodic audits and reviews. Continuously update AML protocols and detection thresholds. | Compliance Officer
Security/ Fraud Risks | Cyberattacks/Data Breaches: Cyberattacks or data breaches exploiting system vulnerabilities may lead to severe financial loss, lawsuits, and lasting damage to the bank’s reputation. | Low | High | Deploy advanced cybersecurity measures. Ensure continuous monitoring and incident response planning. Conduct regular penetration tests and vulnerability assessments. | Cybersecurity Team
Security/ Fraud Risks | Increase in Check Fraud Cases: Inaccuracies in fraud detection systems may lead to an increase in check fraud resulting in financial loss and increased regulatory attention. | Medium | High | Regularly calibrate fraud detection algorithms. Enhance data analytics capabilities. Review and update security protocols frequently. | Cybersecurity & Fraud Prevention Manager
Customer/ User Risks | Low Adoption Due to Poor Usability: A poorly designed user interface may deter customers from using the mobile deposit feature, leading to low adoption and reduced digital revenue. | High | High | Conduct iterative user experience testing; incorporate user feedback Deploy phased rollouts and provide robust customer support. | Product Development Team
Customer/ User Risks | Negative Reviews Impacting Reputation: Unsatisfactory user experiences may generate negative online reviews, which can damage the bank’s reputation over time. | Low | Medium | Proactively manage customer feedback. Implement rapid bug fixes and app updates. Enhance customer service and reputation management strategies. | Customer Service Team
Vendor/ Third-Party Risks | Vendor Delays: External vendors might occasionally delay delivery of key technical or security components which could cause minor schedule adjustments with minimal budget impact. | High | Low | Set clear SLAs and maintain open lines of communication. Include buffer periods in project timelines. Conduct regular vendor performance reviews. | Project Manager
System Performance Risks | Minor System Hiccups: Occasional performance issues during peak loads or maintenance periods. This may lead to brief service disruptions without significant impact on overall KPIs. | Low | Low | Employ proactive system monitoring. Schedule regular maintenance. Prepare quick-response protocols to minimize downtime. | IT Operations
Internal Communication Risks | Communication Gaps: Occasional miscommunications or coordination gaps among cross-functional teams can cause minor delays or misunderstandings in project deliverables. | Low | Low | Hold regular team meetings. Utilize clear communication channels and collaborative tools. Document roles and responsibilities explicitly. | Project Manager
Regulatory Updates Risks | Minor Regulatory Changes: New minor regulatory updates may require small adjustments to processes, necessitating minimal changes to project deliverables. | Low | Low | Continuously monitor regulatory developments. Maintain flexible compliance processes. Update policies promptly when needed. | Compliance Officer
User Interface Usability Risks | Minor UI Issues: Small user interface glitches may occur post-launch.This might slightly impact user satisfaction but can be resolved quickly to minimize disruption | High | Low | Gather ongoing user feedback. Deploy rapid fixes and iterative improvements. Maintain a robust post-launch support system. | UI/UX Team
References
Sienkiewicz, A. (2022, June 20). Project risk assessment: An example with a risk matrix template. BigPicture. https://bigpicture.one/blog/project-risk-assessment-examples/
ECLIPSE Suite. (2022, July 1). Risk severity: Definition, calculation, and reduction. https://www.eclipsesuite.com/risk-severity/
Vicente, V. (2024, February 15). Risk assessment matrix: Overview and guide. AuditBoard. https://www.auditboard.com/blog/what-is-a-risk-assessment-matrix/